## Revision Log
REVISION LOG: LIMS Opportunity For Improvement Log
Revision Number | Date | Comments | Author | Function
0 | 2019-11-18 | Initial creation of spreadsheet | Robert A. Maldonado | Engineering Lab Technician, Generalist
1 | 2020-03-27 | Moved 2019 OFI's to separate sheet for record retention | Robert A. Maldonado | Engineering Lab Technician, Generalist
2 | 2021-01-20 | Moved 2020 OFI's to separate sheet for record retention. Added the following fields for tracking / visibility: "Last Reviewed By:", "Date of Review:", "Last Edited By:", & "Date of Revision" | Robert A. Maldonado | Associate Metrology Engineer

## 2019-OFI-L
Opportunity for Improvement - Impact Legend
High | Opportunity impact is large and can drastically improve quality of laboratory quality / management system
Medium | Opportunity impact can make a difference that is noticeable but may not directly affect all personnel
Low | Opportunity impact is minimal and can be implemented at a date after all other high impact items are identified
Dwyer Instruments, Inc. - Michigan City: Engineering Laboratory - LIMS Opportunity for Improvement Log
Originator | Date Generated | OFI# | Opportunity Description | Opportunity Rationale | Opportunity Impact | Data/Information in Favor of Opportunity | Date of Implementation | Notes | Status (Reserved, To Be Review, Unfinished, In-Progress, Completed, Closed)
Roger Shumaker | 2019-12-20 | 2019-DWYOFI-0001 | When LIMS generates email notification automatically add link directly to spreadsheet log. | To save time jumping out of email, going to LIMS program, logging into the program, then drilling through menus to see the complaint. | Low - Very important for the management group of the LIMS program | NA |  |  | To Be Reviewed
Roger Shumaker | 2019-12-20 | 2019-DWYOFI-0002 | Complete the data acq section of LIMS software | Provide support to run automated data collection of test units. | Medium - would replace current software but provide integrated data sheet generation to eliminate the current manual process. | NA |  |  | To Be Reviewed
Roger Shumaker | 2019-12-30 | 2019-DWYOFI-0003 | Update TC-00032 | Improve the test procedure | Medium - Keep personel from using equipment that is out of cal and other changes. | Markup of document provided to Robert for update. |  |  | To Be Reviewed

## 2020-OFI-L
Opportunity for Improvement - Impact Legend
High | Opportunity impact is large and can drastically improve quality of laboratory quality / management system
Medium | Opportunity impact can make a difference that is noticeable but may not directly affect all personnel
Low | Opportunity impact is minimal and can be implemented at a date after all other high impact items are identified
Dwyer Instruments, Inc. - Michigan City: Engineering Laboratory - LIMS Opportunity for Improvement Log
Originator | Date Generated | OFI# | Opportunity Description | Opportunity Rationale | Opportunity Impact | Data/Information in Favor of Opportunity | Date of Implementation | Notes | Status (Reserved, To Be Review, Unfinished, In-Progress, Completed, Closed)
Roger Shumaker | 2020-01-08 | 2020-DWYOFI-0001 | LIMS update | LIMS needs to be able to print reports for MC6 base unit calibrations | High | Cannot do MC6 base unit calibrations until this is complete. |  |  | To Be Reviewed
Roger Shumaker | 2020-01-08 | 2020-DWYOFI-0002 | LIMS update | LIMS program needs to be able to accept multiple pages of test readings and generate a report. | High | Cannot do DMM calibrations until the program is updated. |  |  | To Be Reviewed
Roger Shumaker | 2020-01-22 | 2020-DWYOFI-0003 | 5522A needs to be added as equipment to LIMS system | So it can be imported for MC6 calibrations | High | - | 2020-03-19 | New method for exporting M&TE from TrackPro and importing into LIMS has been updated. Equipment list using new method is updated weekly. Signed: Robert Maldonado | Completed
Roger Shumaker | 2020-01-22 | 2020-DWYOFI-0004 | Add alicat masters and accuracys to the LIMS program so reports are automatically filled out correctly. | Time savings, no manual labor to alter reports | High | - | 2020-03-27 | M-nSLPM-D/5M and MC-nSLPM-D/5M have been added to database of description and accuracy. When model is input into certificate, description and accuracy should autopopulate. Signed: Robert Maldonado | Completed
Roger Shumaker | 2020-01-22 | 2020-DWYOFI-0005 | LIMS bug, acts like OFI input isn't recorded, after submit button is pushed busy icon continually spins. | Bug | Low | OFI gets submitted, but no notification is actually sent out via email to notify personnel of OFI addition. | 2020-05-05 | It appears that Dwyer IT permissions removed the App permissions that allowed my email to send out notifications. I will see if the App Permissions are removed once again. If it happens, I will need to create a new email to ensure two factor authentication is not a problem. | Completed
Roger Shumaker | 2020-01-31 | 2020-DWYOFI-0006 | Replace TSI with EE75 | Increase accuracy from 2% of reading + .5% FS (10000 FPM) to 1% of reading +.5% FS (8000 FPM) | High | - |  |  | To Be Reviewed
Roger Shumaker | 2020-02-21 | 2020-DWYOFI-0007 | Add south bend | It's a plant | Medium | Needs done. | 2020-03-27 | Internal Customer P00 - South Bend has been added to list of selectable internal customers when generating certificate of calibration documentation. - Signed: Robert Maldonado | Completed
Roger Shumaker | 2020-06-11 | 2020-DWYOFI-0008 | Add entry line for wed ID number. When calibration is complete automatically add entry to the corporate web ID plateform. | Automates entry so it is not forgotten and saves technician time from opening another program to update it. | HIGH, Required by end of year. | Requested by lab manager. |  |  | To Be Reviewed
Roger Shumaker | 2020-06-11 | 2020-DWYOFI-0009 | Provide area for RMA entry into the LIMS program. | With a single entry interface it would reduce the technician time by 66%. Once the information is entered into LIMS, the program could automatically copy those entries in to the Magento program, TFS software, and the Engineering lab RMA database. | HIGH, requested by year end 2020. | Requested by the lab manager. |  |  | To Be Reviewed
Roger Shumaker | 2020-07-21 | 2020-DWYOFI-0010 | Add option to show history of enviromental conditions in the labs. | Was requested by Rocco while Robert was on vacation. Robert currently only one with access. | low | none |  |  | To Be Reviewed

## OFI-L
Opportunity for Improvement - Impact Legend | [7 empty] | Last Edited By: | Robert Maldonado
High | Opportunity impact is large and can drastically improve quality of laboratory quality / management system | [6 empty] | Revision Date: | 2021-01-20
Medium | Opportunity impact can make a difference that is noticeable but may not directly affect all personnel | [6 empty] | Last Reviewed By: | Robert Maldonado
Low | Opportunity impact is minimal and can be implemented at a date after all other high impact items are identified | [6 empty] | Date of Review: | 2021-01-20
Dwyer Instruments, Inc. - Michigan City: Engineering Laboratory - LIMS Opportunity for Improvement Log
Originator | Date Generated | OFI# | Opportunity Description | Opportunity Rationale | Opportunity Impact | Data/Information in Favor of Opportunity | Date of Implementation | Notes | Status (Reserved, To Be Review, Unfinished, In-Progress, Completed, Closed)
Robert Maldonado | 2021-01-20 | 2021-DWYOFI-0001 | Test | Test | Test | Test |  |  | To Be Reviewed